## SUMMARY
Suprv'g. Consultant : |  |  |  |  | THE KINGDOM OF SAUDI ARABIA |  |  |  |  | Contractor :
DAR AL HANDASAH |  |  |  |  | MINISTRY OF TRANSPORT |  |  |  |  | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE - RAMP 2 | [5 empty] | Page: __1_ of _2_
Item : |  |  |  | 20601 |  | SUBGRADE |  |  |  |  | Drwg. No. ________
|  |  |  | 3030101 |  | AGGREGATE BASE COURSE
|  |  |  | 4020102 |  | PRIME COAT (mc1)
|  |  |  | 4050101 |  | BIT. BASE COURSE
|  |  |  | 4050301 |  | BIT. WEARING COURSE
SUMMARY
ITEM NO. |  | DESCRIPTION |  |  |  |  | UNIT | TOTAL |  |  |  | REMARKS
20601 |  | SUBGRADE |  |  |  |  | M³ | 3538.8921
3030101 |  | AGGREGATE BASE COURSE |  |  |  |  | M³ | 1603.8067
4020102 |  | PRIME COAT (mc1) |  |  |  |  | M² | 5144.8024
4050101 |  | BIT. BASE COURSE |  |  |  |  | M³ | 980.6677
4050301 |  | BIT. WEARING COURSE |  |  |  |  | M³ | 240.1554
Suprv'g. Consultant : | [8 empty] | Contractor :
| DAR AL HANDASAH |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE - RAMP 2 |  |  |  | AL RAHJI ALLIANCE
Quantity Surveyor |  |  | Res. Engineer | [5 empty] | Quantity Surveyor |  |  | Proj. Manager

## ASFORM
Suprv'g. Consultant : | [5 empty] | THE KINGDOM OF SAUDI ARABIA | [11 empty] | Contractor :
DAR AL HANDASAH | [5 empty] | MINISTRY OF TRANSPORT | [11 empty] | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  | HHR - AIR DEFENSE INTERCHANGE - RAMP 2 | [15 empty] | Page: _2__ of __2__
Item : |  |  |  |  | 20601 |  |  |  |  | SUBGRADE | [9 empty] | Drwg. No. ________
[5 empty] | 3030101 |  |  |  |  | AGGREGATE BASE COURSE
[5 empty] | 4020102 |  |  |  |  | PRIME COAT (mc1)
[5 empty] | 4050101 |  |  |  |  | BIT. BASE COURSE
[5 empty] | 4050301 |  |  |  |  | BIT. WEARING COURSE
| VAR. 1 |  |  |  | 0.5 | 1.5 |  |  |  |  | W |  |  |  |  | 2.5 | 0.5 | VAR. 2
|  |  |  | 0.3 | [6 empty] | Carriageway | [6 empty] | 0.3
S.E.
|  | 6 | : 1 | [16 empty] | 6 | :1
0.85
[14 empty] | 0.05 | Bituminous Wearing Course
Bituminous Tack Coat
| Note: | [12 empty] | 0.2 | Bituminous Base Course
| Rounding is already deducted in subgrade computation. | [13 empty] | Bituminous Prime Coat
[14 empty] | 0.3 | Aggregate Base Course | [5 empty] | Rounding Left= |  |  |  | 0.0079
[14 empty] | 0.3 | Sub-grade | [5 empty] | Rounding Right= |  |  |  | 0.0061
STATION |  | DIST. (m.) |  | WIDTH |  | AVE. WIDTH | SUPER ELEVATION | VARIABLE 1 | VARIABLE 2 | SUB-GRADE |  |  | AGG. BASE COURSE |  | PRIME COAT |  |  | BIT. BASE COURSE |  |  | BIT. WEARING COURSE |  |  | REMARKS
[10 empty] | 0.3 |  |  | 0.3 |  | ( W | + |  | 0.2 |  |  | 0.05
[10 empty] | VAR |  | x D | 1.62 | x D | 4.9 |  | x D | 0.86 |  | x D | 0.2025 |  | x D
[10 empty] | VAR |  | x D | 0.96 | x D | 2.95 |  | x D | 0.53 |  | x D | 0.1263 |  | x D | Vertical left
[10 empty] | VAR |  | x D | 0.66 | x D | 1.95 |  | x D | 0.33 |  | x D | 0.0763 |  | x D | Vertical right
[10 empty] | (Cu. m.) |  |  | (Cu. m). |  | (Sq.. m). |  |  | (Cu. m). |  |  | (Cu. m).
RAMP 2
0 |  |  |  | 3.994 |  |  | 1.5% | 4.6789 | 5.6044
|  | 57.407 |  |  |  | 4.158 |  |  |  | 266.632 |  |  | 126.7202 |  | 408.049 |  |  | 78.1654 |  |  | 19.1854 |  |  | Vertical left
57.407 |  |  |  | 4.322 |  |  | 1.682% | 4.6324 | 5.6725
|  | 207.143 |  |  |  | 4.661 |  |  |  | 1007.8167 |  |  | 488.5053 |  | 1576.5654 |  |  | 302.8845 |  |  | 74.4368 |  |  | Vertical left
264.55 |  |  |  | 5 |  |  | 2.34% | 4.4721 | 5.933
|  | 25.877 |  |  |  | 6.3785 |  |  |  | 140.6654 |  |  | 74.3589 |  | 241.3936 |  |  | 46.7261 |  |  | 11.5211 |  |  | Vertical left
290.427 |  |  |  | 7.757 |  |  | 2.34% | 4.4721 | 5.933
|  | 16.348 |  |  |  | 9.311 |  |  |  | 103.2487 |  |  | 61.3589 |  | 200.4428 |  |  | 39.1077 |  |  | 9.6756 |  |  | Vertical left
306.775 |  |  |  | 10.865 |  |  | 2.34% | 4.4721 | 5.933
|  | 0 |  |  |  | 7.9325 |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
306.775 |  |  |  | 5 |  |  | 2.34% | 4.4721 | 5.933
|  | 70.326 |  |  |  | 5 |  |  |  | 525.7338 |  |  | 219.4171 |  | 696.2274 |  |  | 130.8064 |  |  | 31.8225
377.101 |  |  |  | 5 |  |  | 2.34% | 4.4721 | 5.933
|  | 142.615 |  |  |  | 5 |  |  |  | 1094.7024 |  |  | 444.9588 |  | 1411.8885 |  |  | 265.2639 |  |  | 64.5333
519.716 |  |  |  | 5 |  |  | 5.3% | 3.8695 | 7.478
|  | 0 |  |  |  | 7.4825 |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
519.716 |  |  |  | 9.965 |  |  | 5.3% | 3.8695 | 7.478
|  | 21.771 |  |  |  | 7.867 |  |  |  | 142.3627 |  |  | 72.2819 |  | 235.4969 |  |  | 45.7931 |  |  | 11.3133 |  |  | Vertical left
541.487 |  |  |  | 5.769 |  |  | 5.3% | 3.8695 | 7.478
|  | 7.275 |  |  |  | 5.3845 |  |  |  | 41.6222 |  |  | 18.7357 |  | 60.6335 |  |  | 11.6902 |  |  | 2.8774 |  |  | Vertical left
548.762 |  |  |  | 5 |  |  | 4.752% | 3.9685 | 7.1341
|  | 43.176 |  |  |  | 4.325 |  |  |  | 216.108 |  |  | 97.4698 |  | 314.1054 |  |  | 60.2305 |  |  | 14.7899 |  |  | Vertical left
591.938 |  |  |  | 3.65 |  |  | 1.5% | 4.6789 | 5.6044
SUB-TOTAL | [9 empty] | 3538.8921 |  |  | 1603.8067 |  | 5144.8024 |  |  | 980.6677 |  |  | 240.1554
Suprv'g. Consultant : | [6 empty] | HHR - AIR DEFENSE INTERCHANGE - RAMP 2 | [10 empty] | Contractor :
DAR AL HANDASAH | [18 empty] | AL RAHJI ALLIANCE
Quantity Surveyor |  |  |  | Res. Engineer | [13 empty] | Quantity Surveyor |  |  |  | Proj. Manager
C
L