## SUMMARY
Suprv'g. Consultant : |  |  |  |  | THE KINGDOM OF SAUDI ARABIA |  |  |  |  | Contractor :
DAR AL HANDASAH |  |  |  |  | MINISTRY OF TRANSPORT |  |  |  |  | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE - RAMP 3 | [5 empty] | Page: __1_ of _2_
Item : |  |  |  | 20601 |  | SUBGRADE |  |  |  |  | Drwg. No. ________
|  |  |  | 3030101 |  | AGGREGATE BASE COURSE
|  |  |  | 4020102 |  | PRIME COAT (mc1)
|  |  |  | 4050101 |  | BIT. BASE COURSE
|  |  |  | 4050301 |  | BIT. WEARING COURSE
SUMMARY
ITEM NO. |  | DESCRIPTION |  |  |  |  | UNIT | TOTAL |  |  |  | REMARKS
20601 |  | SUBGRADE |  |  |  |  | M³ | 6996.3483
3030101 |  | AGGREGATE BASE COURSE |  |  |  |  | M³ | 3314.2899
4020102 |  | PRIME COAT (mc1) |  |  |  |  | M² | 10665.4306
4050101 |  | BIT. BASE COURSE |  |  |  |  | M³ | 2041.3576
4050301 |  | BIT. WEARING COURSE |  |  |  |  | M³ | 500.7958
Suprv'g. Consultant : | [8 empty] | Contractor :
| DAR AL HANDASAH |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE - RAMP 3 |  |  |  | AL RAHJI ALLIANCE
Quantity Surveyor |  |  | Res. Engineer | [5 empty] | Quantity Surveyor |  |  | Proj. Manager

## ASFORM
Suprv'g. Consultant : | [5 empty] | THE KINGDOM OF SAUDI ARABIA | [11 empty] | Contractor :
DAR AL HANDASAH | [5 empty] | MINISTRY OF TRANSPORT | [11 empty] | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  | HHR - AIR DEFENSE INTERCHANGE - RAMP 3 | [15 empty] | Page: _2__ of __2__
Item : |  |  |  |  | 20601 |  |  |  |  | SUBGRADE | [9 empty] | Drwg. No. ________
[5 empty] | 3030101 |  |  |  |  | AGGREGATE BASE COURSE
[5 empty] | 4020102 |  |  |  |  | PRIME COAT (mc1)
[5 empty] | 4050101 |  |  |  |  | BIT. BASE COURSE
[5 empty] | 4050301 |  |  |  |  | BIT. WEARING COURSE
| VAR. 1 |  |  |  | 0.5 | 1.5 |  |  |  |  | W |  |  |  |  | 2.5 | 0.5 | VAR. 2
|  |  |  | 0.3 | [6 empty] | Carriageway | [6 empty] | 0.3
S.E.
|  | 6 | : 1 | [16 empty] | 6 | :1
0.85
[14 empty] | 0.05 | Bituminous Wearing Course
Bituminous Tack Coat
| Note: | [12 empty] | 0.2 | Bituminous Base Course
| Rounding is already deducted in subgrade computation. | [13 empty] | Bituminous Prime Coat
[14 empty] | 0.3 | Aggregate Base Course | [5 empty] | Rounding Left= |  |  |  | 0.0079
[14 empty] | 0.3 | Sub-grade | [5 empty] | Rounding Right= |  |  |  | 0.0061
STATION |  | DIST. (m.) |  | WIDTH |  | AVE. WIDTH | SUPER ELEVATION | VARIABLE 1 | VARIABLE 2 | SUB-GRADE |  |  | AGG. BASE COURSE |  | PRIME COAT |  |  | BIT. BASE COURSE |  |  | BIT. WEARING COURSE |  |  | REMARKS
[10 empty] | 0.3 |  |  | 0.3 |  | ( W | + |  | 0.2 |  |  | 0.05
[10 empty] | VAR |  | x D | 1.62 | x D | 4.9 |  | x D | 0.86 |  | x D | 0.2025 |  | x D
[10 empty] | VAR |  | x D | 0.96 | x D | 2.95 |  | x D | 0.53 |  | x D | 0.1263 |  | x D | Vertical left
[10 empty] | VAR |  | x D | 0.66 | x D | 1.95 |  | x D | 0.33 |  | x D | 0.0763 |  | x D | Vertical right
[10 empty] | (Cu. m.) |  |  | (Cu. m). |  | (Sq.. m). |  |  | (Cu. m). |  |  | (Cu. m).
RAMP 3
0 |  |  |  | 7.3 |  |  | 5.3% | 3.8695 | 7.478
|  | 63.159 |  |  |  | 8.0955 |  |  |  | 423.9197 |  |  | 214.0237 |  | 697.6227 |  |  | 135.735 |  |  | 33.5422 |  |  | Vertical left
63.159 |  |  |  | 8.891 |  |  | 6% | 3.75 | 7.9688
|  | 35.219 |  |  |  | 11.038 |  |  |  | 271.1507 |  |  | 150.4344 |  | 492.6434 |  |  | 96.4155 |  |  | 23.8855 |  |  | Vertical left
98.378 |  |  |  | 13.185 |  |  | 6% | 3.75 | 7.9688
|  | 0 |  |  |  | 10.2425 |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
98.378 |  |  |  | 7.3 |  |  | 6% | 3.75 | 7.9688
|  | 74.891 |  |  |  | 7.3 |  |  |  | 653.3483 |  |  | 285.3347 |  | 913.6702 |  |  | 173.7471 |  |  | 42.5006
173.269 |  |  |  | 7.3 |  |  | 6% | 3.75 | 7.9688
|  | 88 |  |  |  | 7.3 |  |  |  | 739.3096 |  |  | 335.28 |  | 1073.6 |  |  | 204.16 |  |  | 49.94
261.269 |  |  |  | 7.3 |  |  | 0% | 5.1 | 5.1
|  | 79 |  |  |  | 7.3 |  |  |  | 658.2861 |  |  | 300.99 |  | 963.8 |  |  | 183.28 |  |  | 44.8325
340.269 |  |  |  | 7.3 |  |  | -5.4% | 7.5444 | 3.852
|  | 116.628 |  |  |  | 7.3 |  |  |  | 1001.4811 |  |  | 444.3527 |  | 1422.8616 |  |  | 270.577 |  |  | 66.1864
456.897 |  |  |  | 7.3 |  |  | -5.4% | 7.5444 | 3.852
|  | 79 |  |  |  | 7.3 |  |  |  | 658.2861 |  |  | 300.99 |  | 963.8 |  |  | 183.28 |  |  | 44.8325
535.897 |  |  |  | 7.3 |  |  | 0% | 5.1 | 5.1
|  | 81 |  |  |  | 7.3 |  |  |  | 674.9515 |  |  | 308.61 |  | 988.2 |  |  | 187.92 |  |  | 45.9675
616.897 |  |  |  | 7.3 |  |  | 5.4% | 3.852 | 7.5444
|  | 118.941 |  |  |  | 7.3 |  |  |  | 1021.3428 |  |  | 453.1652 |  | 1451.0802 |  |  | 275.9431 |  |  | 67.499
735.838 |  |  |  | 7.3 |  |  | 5.4% | 3.852 | 7.5444
|  | 12.819 |  |  |  | 7.3 |  |  |  | 109.1562 |  |  | 48.8404 |  | 156.3918 |  |  | 29.7401 |  |  | 7.2748
748.657 |  |  |  | 7.3 |  |  | 4.644% | 3.9886 | 7.07
|  | 0 |  |  |  | 9.779 |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
748.657 |  |  |  | 12.258 |  |  | 4.644% | 3.9886 | 7.07
|  | 78.798 |  |  |  | 9.909 |  |  |  | 516.8893 |  |  | 309.8889 |  | 1013.2635 |  |  | 197.9248 |  |  | 48.9927 |  |  | Vertical left
827.455 |  |  |  | 7.56 |  |  | 0% | 5.1 | 5.1
|  | 24.545 |  |  |  | 7.465 |  |  |  | 130.5393 |  |  | 78.5317 |  | 255.6362 |  |  | 49.6545 |  |  | 12.2615 |  |  | Vertical left
852 |  |  |  | 7.37 |  |  | -1.5% | 5.6044 | 4.6789
|  | 26.53 |  |  |  | 7.335 |  |  |  | 137.6876 |  |  | 83.8481 |  | 272.861 |  |  | 52.9804 |  |  | 13.0806 |  |  | Vertical left
878.53 |  |  |  | 7.3 |  |  | -1.5% | 5.6044 | 4.6789
SUB-TOTAL | [9 empty] | 6996.3483 |  |  | 3314.2899 |  | 10665.4306 |  |  | 2041.3576 |  |  | 500.7958
Suprv'g. Consultant : | [6 empty] | HHR - AIR DEFENSE INTERCHANGE - RAMP 3 | [10 empty] | Contractor :
DAR AL HANDASAH | [18 empty] | AL RAHJI ALLIANCE
Quantity Surveyor |  |  |  | Res. Engineer | [13 empty] | Quantity Surveyor |  |  |  | Proj. Manager
C
L