## SUMMARY
Suprv'g. Consultant : |  |  |  |  | THE KINGDOM OF SAUDI ARABIA |  |  |  |  | Contractor :
DAR AL HANDASAH |  |  |  |  | MINISTRY OF TRANSPORT |  |  |  |  | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE- RAMP 6 | [5 empty] | Page: __1_ of _2_
Item : |  |  |  | 20601 |  | SUBGRADE |  |  |  |  | Drwg. No. ________
|  |  |  | 3030101 |  | AGGREGATE BASE COURSE
|  |  |  | 4020102 |  | PRIME COAT (mc1)
|  |  |  | 4050101 |  | BIT. BASE COURSE
|  |  |  | 4050301 |  | BIT. WEARING COURSE
SUMMARY
ITEM NO. |  | DESCRIPTION |  |  |  |  | UNIT | TOTAL |  |  |  | REMARKS
20601 |  | SUBGRADE |  |  |  |  | M³ | 2776.9618
3030101 |  | AGGREGATE BASE COURSE |  |  |  |  | M³ | 1214.2958
4020102 |  | PRIME COAT (mc1) |  |  |  |  | M² | 3874.9458
4050101 |  | BIT. BASE COURSE |  |  |  |  | M³ | 733.5395
4050301 |  | BIT. WEARING COURSE |  |  |  |  | M³ | 179.0719
Suprv'g. Consultant : | [8 empty] | Contractor :
| DAR AL HANDASAH |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE- RAMP 6 |  |  |  | AL RAHJI ALLIANCE
Quantity Surveyor |  |  | Res. Engineer | [5 empty] | Quantity Surveyor |  |  | Proj. Manager

## ASFORM
Suprv'g. Consultant : | [5 empty] | THE KINGDOM OF SAUDI ARABIA | [11 empty] | Contractor :
DAR AL HANDASAH | [5 empty] | MINISTRY OF TRANSPORT | [11 empty] | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  | HHR - AIR DEFENSE INTERCHANGE- RAMP 6 | [15 empty] | Page: _2__ of __2__
Item : |  |  |  |  | 20601 |  |  |  |  | SUBGRADE | [9 empty] | Drwg. No. ________
[5 empty] | 3030101 |  |  |  |  | AGGREGATE BASE COURSE
[5 empty] | 4020102 |  |  |  |  | PRIME COAT (mc1)
[5 empty] | 4050101 |  |  |  |  | BIT. BASE COURSE
[5 empty] | 4050301 |  |  |  |  | BIT. WEARING COURSE
| VAR. 1 |  |  |  | 0.5 | 1.5 |  |  |  |  | W |  |  |  |  | 2.5 | 0.5 | VAR. 2
|  |  |  | 0.3 | [6 empty] | Carriageway | [6 empty] | 0.3
S.E.
|  | 6 | : 1 | [16 empty] | 6 | :1
0.85
[14 empty] | 0.05 | Bituminous Wearing Course
Bituminous Tack Coat
| Note: | [12 empty] | 0.2 | Bituminous Base Course
| Rounding is already deducted in subgrade computation. | [13 empty] | Bituminous Prime Coat
[14 empty] | 0.3 | Aggregate Base Course | [5 empty] | Rounding Left= |  |  |  | 0.0079
[14 empty] | 0.3 | Sub-grade | [5 empty] | Rounding Right= |  |  |  | 0.0061
STATION |  | DIST. (m.) |  | WIDTH |  | AVE. WIDTH | SUPER ELEVATION | VARIABLE 1 | VARIABLE 2 | SUB-GRADE |  |  | AGG. BASE COURSE |  | PRIME COAT |  |  | BIT. BASE COURSE |  |  | BIT. WEARING COURSE |  |  | REMARKS
[10 empty] | 0.3 |  |  | 0.3 |  | ( W | + |  | 0.2 |  |  | 0.05
[10 empty] | VAR |  | x D | 1.62 | x D | 4.9 |  | x D | 0.86 |  | x D | 0.2025 |  | x D
[10 empty] | VAR |  | x D | 0.96 | x D | 2.95 |  | x D | 0.53 |  | x D | 0.1263 |  | x D | Vertical left
[10 empty] | VAR |  | x D | 0.66 | x D | 1.95 |  | x D | 0.33 |  | x D | 0.0763 |  | x D | Vertical right
[10 empty] | (Cu. m.) |  |  | (Cu. m). |  | (Sq.. m). |  |  | (Cu. m). |  |  | (Cu. m).
RAMP 6
0 |  |  |  | 3.65 |  |  | -1.5% | 5.6044 | 4.6789
|  | 39.483 |  |  |  | 4.325 |  |  |  | 170.1425 |  |  | 89.1329 |  | 287.2388 |  |  | 55.0788 |  |  | 13.5249 |  |  | Vertical left
39.483 |  |  |  | 5 |  |  | -1.1% | 5.4604 | 4.7842
|  | 10.517 |  |  |  | 5.3925 |  |  |  | 49.6296 |  |  | 27.1102 |  | 87.7381 |  |  | 16.9166 |  |  | 4.1639 |  |  | Vertical left
50 |  |  |  | 5.785 |  |  | 0% | 5.1 | 5.1
|  | 31.64 |  |  |  | 8.322 |  |  |  | 188.3346 |  |  | 109.3668 |  | 356.6461 |  |  | 69.4308 |  |  | 17.1615 |  |  | Vertical left
81.64 |  |  |  | 10.859 |  |  | 3.494% | 4.2161 | 6.4528
|  | 0 |  |  |  | 7.9295 |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
81.64 |  |  |  | 5 |  |  | 3.494% | 4.2161 | 6.4528
|  | 16.36 |  |  |  | 5 |  |  |  | 126.6653 |  |  | 51.0432 |  | 161.964 |  |  | 30.4296 |  |  | 7.4029
98 |  |  |  | 5 |  |  | 5.4% | 3.852 | 7.5444
|  | 113.056 |  |  |  | 5 |  |  |  | 892.7998 |  |  | 352.7347 |  | 1119.2544 |  |  | 210.2842 |  |  | 51.1578
211.056 |  |  |  | 5 |  |  | 5.4% | 3.852 | 7.5444
|  | 54.574 |  |  |  | 5 |  |  |  | 418.0606 |  |  | 170.2709 |  | 540.2826 |  |  | 101.5076 |  |  | 24.6947
265.63 |  |  |  | 5 |  |  | 1.5% | 4.6789 | 5.6044
|  | 96.066 |  |  |  | 5.588 |  |  |  | 730.1307 |  |  | 316.672 |  | 1007.5402 |  |  | 189.9801 |  |  | 46.2942
361.696 |  |  |  | 6.176 |  |  | 1.5% | 4.6789 | 5.6044
|  | 3.676 |  |  |  | 6.393 |  |  |  | 28.8265 |  |  | 13.0053 |  | 41.5131 |  |  | 7.8615 |  |  | 1.9194
365.372 |  |  |  | 6.61 |  |  | 1.5% | 4.6789 | 5.6044
|  | 3.554 |  |  |  | 5.805 |  |  |  | 15.4808 |  |  | 8.5349 |  | 27.5613 |  |  | 5.299 |  |  | 1.3027 |  |  | vertical right
368.926 |  |  |  | 5 |  |  | 1.5% | 4.6789 | 5.6044
|  | 0.712 |  |  |  | 5.7845 |  |  |  | 3.097 |  |  | 1.7055 |  | 5.507 |  |  | 1.0587 |  |  | 0.26025 |  |  | vertical right
369.638 |  |  |  | 6.569 |  |  | 1.5% | 4.6789 | 5.6044
|  | 3.297 |  |  |  | 5.7845 |  |  |  | 14.3411 |  |  | 7.8975 |  | 25.5006 |  |  | 4.9023 |  |  | 1.2051 |  |  | vertical right
372.935 |  |  |  | 5 |  |  | 1.5% | 4.6789 | 5.6044
|  | 4.45 |  |  |  | 8.9125 |  |  |  | 23.5322 |  |  | 14.8352 |  | 48.3381 |  |  | 9.4006 |  |  | 2.3226 |  |  | vertical right
377.385 |  |  |  | 12.825 |  |  | 1.5% | 4.6789 | 5.6044
|  | 3.203 |  |  |  | 9.699 |  |  |  | 28.294 |  |  | 14.5086 |  | 46.7606 |  |  | 8.9678 |  |  | 2.2019
380.588 |  |  |  | 6.573 |  |  | 1.5% | 4.6789 | 5.6044
|  | 4.763 |  |  |  | 5.7865 |  |  |  | 36.4839 |  |  | 15.9844 |  | 50.8998 |  |  | 9.6084 |  |  | 2.3426
385.351 |  |  |  | 5 |  |  | 1.5% | 4.6789 | 5.6044
|  | 6.889 |  |  |  | 5 |  |  |  | 51.1433 |  |  | 21.4937 |  | 68.2011 |  |  | 12.8135 |  |  | 3.1173
392.24 |  |  |  | 5 |  |  | 1.5% | 4.6789 | 5.6044
SUB-TOTAL | [9 empty] | 2776.9618 |  |  | 1214.2958 |  | 3874.9458 |  |  | 733.5395 |  |  | 179.0719
Suprv'g. Consultant : | [6 empty] | HHR - AIR DEFENSE INTERCHANGE- RAMP 6 | [10 empty] | Contractor :
DAR AL HANDASAH | [18 empty] | AL RAHJI ALLIANCE
Quantity Surveyor |  |  |  | Res. Engineer | [13 empty] | Quantity Surveyor |  |  |  | Proj. Manager
C
L