## SUMMARY
Suprv'g. Consultant : |  |  |  |  | THE KINGDOM OF SAUDI ARABIA |  |  |  |  | Contractor :
DAR AL HANDASAH |  |  |  |  | MINISTRY OF TRANSPORT |  |  |  |  | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE- SR 2 | [5 empty] | Page: __1_ of _2_
Item : |  |  |  | 20601 |  | SUBGRADE |  |  |  |  | Drwg. No. ________
|  |  |  | 3030101 |  | AGGREGATE BASE COURSE
|  |  |  | 4020102 |  | PRIME COAT (mc1)
|  |  |  | 4050101 |  | BIT. BASE COURSE
|  |  |  | 4050301 |  | BIT. WEARING COURSE
SUMMARY
ITEM NO. |  | DESCRIPTION |  |  |  |  | UNIT | TOTAL |  |  |  | REMARKS
20601 |  | SUBGRADE |  |  |  |  | M³ | 685.9416
3030101 |  | AGGREGATE BASE COURSE |  |  |  |  | M³ | 375.6122
4020102 |  | PRIME COAT (mc1) |  |  |  |  | M² | 1203.6426
4050101 |  | BIT. BASE COURSE |  |  |  |  | M³ | 229.113
4050301 |  | BIT. WEARING COURSE |  |  |  |  | M³ | 56.0692
Suprv'g. Consultant : | [8 empty] | Contractor :
| DAR AL HANDASAH |  |  |  |  | HHR - AIR DEFENSE INTERCHANGE- SR 2 |  |  |  | AL RAHJI ALLIANCE
Quantity Surveyor |  |  | Res. Engineer | [5 empty] | Quantity Surveyor |  |  | Proj. Manager

## ASFORM
Suprv'g. Consultant : | [5 empty] | THE KINGDOM OF SAUDI ARABIA | [12 empty] | Contractor :
DAR AL HANDASAH | [5 empty] | MINISTRY OF TRANSPORT | [12 empty] | AL RAHJI ALLIANCE
GENERAL TECHNICAL ADMINISTRATION
PAVEMENT COMPUTATION
Project : |  |  |  | HHR - AIR DEFENSE INTERCHANGE- SR 2 | [16 empty] | Page: _2__ of __2__
Item : |  |  |  |  | 20601 | [5 empty] | SUBGRADE | [9 empty] | Drwg. No. ________
[5 empty] | 3030101 | [5 empty] | AGGREGATE BASE COURSE
[5 empty] | 4020102 | [5 empty] | PRIME COAT (mc1)
[5 empty] | 4050101 | [5 empty] | BIT. BASE COURSE
[5 empty] | 4050301 | [5 empty] | BIT. WEARING COURSE
| VAR. 1 |  |  |  | 0.5 | 1.5 | [5 empty] | W |  |  |  |  | 1.5 | 0.5 | VAR. 2
|  |  |  | 0.3 | [7 empty] | Carriageway | [6 empty] | 0.3
[9 empty] | S.E. |  |  |  | S.E.
|  | 6 | : 1 | [17 empty] | 6 | :1
0.85
[15 empty] | 0.05 | Bituminous Wearing Course
Bituminous Tack Coat
| Note: | [13 empty] | 0.2 | Bituminous Base Course
| Rounding is already deducted in subgrade computation. | [14 empty] | Bituminous Prime Coat
[15 empty] | 0.3 | Aggregate Base Course | [5 empty] | Rounding Left= |  |  |  | 0.0079
[15 empty] | 0.3 | Sub-grade | [5 empty] | Rounding Right= |  |  |  | 0.0061
STATION |  | DIST. (m.) |  | WIDTH |  | AVE. WIDTH | SUPER ELEVATION | VARIABLE 1 |  | VARIABLE 2 | SUB-GRADE |  |  | AGG. BASE COURSE |  | PRIME COAT |  |  | BIT. BASE COURSE |  |  | BIT. WEARING COURSE |  |  | REMARKS
[11 empty] | 0.3 |  |  | 0.3 |  | ( W | + |  | 0.2 |  |  | 0.05
[11 empty] | VAR |  | x D | 1.32 | x D | 3.9 |  | x D | 0.66 |  | x D | 0.1525 |  | x D
[11 empty] | VAR |  | x D | 0.66 | x D | 1.95 |  | x D | 0.33 |  | x D | 0.0763 |  | x D | Vertical left
[11 empty] | VAR |  | x D | 0.66 | x D | 1.95 |  | x D | 0.33 |  | x D | 0.0763 |  | x D | Vertical right
[11 empty] | (Cu. m.) |  |  | (Cu. m). |  | (Sq. m). |  |  | (Cu. m). |  |  | (Cu. m).
Service Road 2
0 |  |  |  | 3.902 |  |  | 1.5% | 0 |  | 5.6044
|  | 1.567 |  |  |  | 5.5055 |  |  |  |  | 4.7392 |  |  | 3.6224 |  | 11.6828 |  |  | 2.2425 |  |  | 0.55092 |  |  | Vertical left
1.567 |  |  |  | 7.109 |  |  | 1.5% | 0 |  | 5.6044
|  | 0.09 |  |  |  | 7.2045 |  |  |  |  | 0.31807 |  |  | 0.25392 |  | 0.82391 |  |  | 0.15938 |  |  | 0.039287 |  |  | Vertical left
1.657 |  |  |  | 7.3 |  |  | 1.5% | 0 |  | 5.6044
|  | 8.978 |  |  |  | 7.6945 |  |  |  |  | 53.3789 |  |  | 32.5753 |  | 104.0954 |  |  | 19.7417 |  |  | 4.8232
10.635 |  |  |  | 8.089 |  |  | 1.5% | 0 |  | 5.6044
|  | 3.438 |  |  |  | 7.6945 |  |  |  |  | 20.4345 |  |  | 12.4743 |  | 39.8619 |  |  | 7.5598 |  |  | 1.847
14.073 |  |  |  | 7.3 |  |  | 1.5% | 0 |  | 5.6044
|  | 53.658 |  |  |  | 7.3 |  |  |  |  | 365.928 |  |  | 188.3396 |  | 600.9696 |  |  | 113.755 |  |  | 27.768
67.731 |  |  |  | 7.3 |  |  | 1.5% | 4.6789 |  | 5.6044
|  | 5 |  |  |  | 9.7825 |  |  |  |  | 27.4457 |  |  | 17.9738 |  | 58.6625 |  |  | 11.4325 |  |  | 2.8271 |  |  | Vertical right
72.731 |  |  |  | 12.265 |  |  | 1.5% | 4.6789 |  | 0
|  | 2.609 |  |  |  | 9.965 |  |  |  |  | 14.464 |  |  | 9.5215 |  | 31.0862 |  |  | 6.0607 |  |  | 1.499 |  |  | Vertical right
75.34 |  |  |  | 7.665 |  |  | 1.5% | 4.6789 |  | 0
|  | 3.319 |  |  |  | 8.4215 |  |  |  |  | 16.8633 |  |  | 10.5758 |  | 34.423 |  |  | 6.6855 |  |  | 1.6508 |  |  | Vertical right
78.659 |  |  |  | 9.178 |  |  | 1.5% | 4.6789 |  | 0
|  | 0.603 |  |  |  | 8.516 |  |  |  |  | 3.0808 |  |  | 1.9385 |  | 6.311 |  |  | 1.226 |  |  | 0.30277 |  |  | Vertical right
79.262 |  |  |  | 7.854 |  |  | 1.5% | 4.6789 |  | 0
|  | 3.322 |  |  |  | 8.6105 |  |  |  |  | 17.0669 |  |  | 10.7737 |  | 35.082 |  |  | 6.8171 |  |  | 1.6837 |  |  | Vertical right
82.584 |  |  |  | 9.367 |  |  | 1.5% | 4.6789 |  | 0
|  | 0.603 |  |  |  | 8.8315 |  |  |  |  | 3.1379 |  |  | 1.9956 |  | 6.5012 |  |  | 1.2641 |  |  | 0.31228 |  |  | Vertical right
83.187 |  |  |  | 8.296 |  |  | 1.5% | 4.6789 |  | 0
|  | 0.655 |  |  |  | 8.185 |  |  |  |  | 3.2815 |  |  | 2.0407 |  | 6.6384 |  |  | 1.2884 |  |  | 0.31804 |  |  | Vertical right
83.842 |  |  |  | 8.074 |  |  | 1.5% | 4.6789 |  | 5.6044
|  | 21.838 |  |  |  | 8.3495 |  |  |  |  | 155.8029 |  |  | 83.5271 |  | 267.5046 |  |  | 50.8804 |  |  | 12.4471
105.68 |  |  |  | 8.625 |  |  | 1.5% | 0 |  | 5.6044
SUB-TOTAL | [10 empty] | 685.9416 |  |  | 375.6122 |  | 1203.6426 |  |  | 229.113 |  |  | 56.0692
Suprv'g. Consultant : | [6 empty] | HHR - AIR DEFENSE INTERCHANGE- SR 2 | [11 empty] | Contractor :
DAR AL HANDASAH | [19 empty] | AL RAHJI ALLIANCE
Quantity Surveyor |  |  |  | Res. Engineer | [14 empty] | Quantity Surveyor |  |  |  | Proj. Manager
C
L